## Sheet1
Waterfall Gantt Chart Template
Project Title: | Yosemite |  | Start Date: |  | 2024-05-20
Project Manager: | Philipp Lutz |  | Estimated Completion Date: |  | 2024-08-02
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[5 empty] | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F
Build a storefront on the platform | bar: WEEK 9 M to WEEK 12 F
Kickoff Meeting | All | 2024-05-20 | 2024-05-20 | 1 | bar: WEEK 1 M
Build storefront | Aliyah | 2024-05-21 | 2024-06-03 | 10 | bar: WEEK 1 T to WEEK 3 M
Input Inventory Data | Moe | 2024-06-04 | 2024-06-10 | 5 | bar: WEEK 3 T to WEEK 4 M
Status Report 1 | Me | 2024-06-11 | 2024-06-11 | 1 | bar: WEEK 4 T
Engage stakeholders | Lou, me | 2024-05-20 | 2024-06-11 | 17 | bar: WEEK 1 M to WEEK 4 T
Integrate social media | bar: WEEK 9 M to WEEK 12 F
Build social media integration | Aliyah | 2024-06-12 | 2024-06-25 | 10 | bar: WEEK 4 W to WEEK 6 T
Train Stefano’s on platform | Moe | 2024-06-26 | 2024-07-02 | 5 | bar: WEEK 6 W to WEEK 7 T
Create social media channels | Taylor | 2024-07-03 | 2024-07-09 | 5 | bar: WEEK 7 W to WEEK 8 T
Status Report 2 | Me | 2024-07-10 | 2024-07-10 | 1 | bar: WEEK 8 W
Engage stakeholders | Lou, me | 2024-06-12 | 2024-07-10 | 21 | bar: WEEK 4 W to WEEK 8 W
Develop a recommendation engine | bar: WEEK 9 M to WEEK 12 F
Build recommendation engine | Aliyah | 2024-07-11 | 2024-07-24 | 10 | bar: WEEK 8 Tr to WEEK 10 W
Create Custom Sales Report | Moe | 2024-07-25 | 2024-07-31 | 5 | bar: WEEK 10 Tr to WEEK 11 W
Status Report 3 | Me | 2024-08-01 | 2024-08-01 | 1 | bar: WEEK 11 Tr
Closure Meeting | All | 2024-08-02 | 2024-08-02 | 1 | bar: WEEK 11 F
Engage stakeholders | Lou, me | 2024-07-11 | 2024-08-02 | 17 | bar: WEEK 8 Tr to WEEK 11 F
Formulas:
START DATE = WORKDAY([Start Date:, row above],1)
Start Date: = WORKDAY([START DATE], [DURATION]-1)
Start Date: = [Start Date:, row above]